## Sheet1
S.No. | Circle | PLAN ID | Nominal Aop | HOP TYPE | HOP A-B | HOP B-A | District | PROJECT | SITE A ANT DIA | SITE B ANT DIA | Max Ant Size | SITE A NAME | TOCO VENDOR A | TOCO ID A | SITE B NAME | TOCO VENDOR B | TOCO ID B | MEDIA AVAILABILITY STATUS | SR NO SITE A | SR DATE SITE A | SR NO SITE B | SR DATE SITE B | HOP SR DATE | SP DATE SITE A | SP DATE SITE B | HOP SP DATE | SO RELEASED DATE SITE A | SO RELEASED DATE SITE B | HOP SO DATE | RFAI OFFERED DATE SITE A | RFAI OFFERED DATE SITE B | ACTUAL HOP RFAI OFFERED DATE | PARTNER NAME | RFAI SURVEY COMPLETION DATE | MO NUMBER SITE A | MATERIAL TYPE SITE A(SRN, FRESH, FRESH+SRN) | MO DATE SITE A | MO NUMBER SITE B | MATERIAL TYPE SITE B(SRN, FRESH, FRESH+SRN) | MO DATE SITE B | SRN/RMO NUMBER | SRN/RMO DATE | HOP MO DATE | HOP MATERIAL DISPATCH DATE | HOP MATERIAL DELIVERY DATE | MATERIAL DELIVERY STATUS | SITE A INSTALLATION DATE | PTW Number(Site A) | PTW Status A | SITE B INSTALLATION DATE | PTW Number(Site B) | PTW Status B | HOP I&C DATE | Alignment Date | HOP Installation Remarks | VISIBLE IN NMS | NMS VISIBLE DATE | SOFT AT OFFER DATE | SOFT AT ACCEPTANCE DATE | SOFT-AT STATUS | PHY-AT OFFER DATE | PHY-AT ACCEPTANCE DATE | PHY-AT STATUS | BOTH AT STATUS | PRI ISSUE CATEGORY | PRI SITE ID | PRI OPEN DATE | PRI CLOSE DATE | PRI HISTORY | RFI Survey Allocation Date | Descope | Reason of Extra Visit | WCC Received 80% | WCC Received Date 80% | WCC Received 20% | WCC Received Date 20% | WCC Received Date 100% | Survey | Final Partner Survey | Survey Date
1 | UPE | 1234756712457324jghjrgrhjew8643783624hjgwhewj | AOP 24-25 | E-BAND | ALB368-ACNT04 | ACNT04-ALB368 | Prayagraj | Ceragon-Bharti | 0.9 | 0.9 | 0.9 | Patrakarcolony | Indus | IN-1360937 | Patrakarcolony | TVI | ATUPALH1165 | [12 empty] | 2024-12-22 | 2024-12-22 | 2024-12-22 | Jiya | 2024-12-22 | [9 empty] | 2024-12-24 | 2024-12-25 | Received | 2024-12-26 | Approved In Inside |  | 2024-12-26 | Approved In Inside |  | 2024-12-26 | 2024-12-26 | Site done | Yes | 2024-12-26 | 2025-01-02 | 2025-01-02 | Pending | 2025-01-01 | 2025-01-02 | Pending | Yes | - | [7 empty] | Done | 2025-02-21 | Done | 2025-02-21 | 2025-02-21 | #N/A | JIYA
2 | UPE | 456789098765ff456hnn | AOP 24-25 | E-BAND | ALB45-ALBI06 | ALBI06-ALB45 | Prayagraj | Ceragon-Bharti | 1.2 | 0.6 | 1.2 | Darbhanga | Infratel | UERT11223 | Darbhanga | Space Telecom | STIPL-UPE-657 | [12 empty] | 2024-12-21 | 2024-12-21 | 2024-12-21 | Lagom | 2024-12-21 | [9 empty] | 2024-12-24 | 2024-12-25 | Received | 2024-12-26 |  |  | 2024-12-27 |  |  | 2024-12-27 |  | LOS Issue/Mail Approval taken for Installation only |  |  |  |  | Pending |  |  | Pending |  | LOS Issue | [12 empty] | #N/A | LAGOM